## Sheet1
Product Backlog
Feature Name | PRIORITY | POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT # | Assigned
User registration and login (authentication) | Medium | 5 | Yes | Yes | 1,2 | Shane
Travel recommendations | Medium | 5 | Yes | Yes | 2 | Youness
Ability to add photos, text, and location data to travel entries | High | 7 | Yes | Yes | 1 | Joseph
View travel history and statistics | Medium | 4 | Yes | Yes | 2 | Sabin
Search for travel entries by location or keyword | Medium | 5 | Yes | Yes | 1 | Lane
Fast loading times and smooth performance | Low | 1 | No | No
Share travel entries with others via social media | Low | 2 | No | No
Responsive UI that works well on different devices and screen sizes | Low | 1 | No | No
Secure authentication and data storage | Low | 2 | No | No

## Sheet2
Product Backlog
Feature Name | ASSIGNED TO | Start Date | Finish Date | STORY | SPRINT READY | PRIORITY | STORY POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT #
Feature 1 | Member 1 | 2023-03-09 | 2023-03-19 | Yes | Yes | High | 8 | Yes |  | 1
Feature 2 | Member 2 | 2023-03-10 | 2023-03-20 | No | Yes | Medium | 16 | No |  | 1
Feature 3 | Member 3 | 2023-03-11 | 2023-03-21 | Yes | Yes | Low | 0 | Yes |  | 2