## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Authentication | 5 | Shane Li | 6 | 0 | 0 | 0 | 0 | 0 | 5 | Doing | 5
Google Authentication Setup | 2 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | Done | 3
Create Login Page | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Done | 1
Verify App on Google Cloud Console | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Doing | 0
Upload and download data with MySQL | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Done | 1
Search | 5 | Lane Brantley | 6 | 0 | 0 | 0 | 0 | 0 | 5 | Done | 5
Search Bar | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | Done | 3
Link to MySQL Database | 2 |  | 3 | 0 | 0 | 0 | 0 | 0 | 2 | Done | 2
Travel Recommendation | 5 | Youness El Badr | 5 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Create Table for Travel Destination | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Link to MySQL Database | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Front (Home- Attraction reviews - Payment -Trip pages | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Images and Style | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Travel History | 4 | Sabin Shrestha | 4 | 0 | 0 | 0 | 0 | 0 | 1 | Doing | 1
Previous flight/ car rental/ accomodation details | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Photo story/ feature | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Create travel itinerary / save itinerary | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Home Page (travel history, image galleries) | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Done | 1
C.E.D Posts | 7 | Joseph Petrongelli | 7 | 0 | 0 | 0 | 0 | 0 | 2.33 | Doing | 2.33
Add/Edit/Remove Text for post | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 1 | Doing | 1
Add/Edit/Remove Image for post | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 1 | Doing | 1
Add/Edit/Remove location data for post | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0.33 | Doing | 0.33
TOTAL |  |  | 28 | 0 | 0 | 0 | 0 | 0 | 13.33 |  | 13.33